## Slide 1: CHALLENGER & HORIZON RENOVATION & ADDITIONS
Capital Projects Advisory Review Board
Project Review Committee
Request for GC/CM Project Delivery Method
September 24, 2020
1

## Slide 2
Project Team
Project Background & Overview
  Traditional delivery method not desirable
Meets Qualifying GC/CM Criteria
  Qualifying Project
  Management Plan
    Project Team
    Schedule
    Budget & Funding
Project Summary
Questions
AGENDA
2

## Slide 3
MUKILTEO SCHOOL DISTRICT
Karen Mooseker, Executive Director of District Support Services
  7 years experience with K-12 construction projects
  GC/CM experience – 4 projects
  Member of Capital Projects Advisory Review Board (CPARB)
Shelly Henderson, Director of Capital Projects
  25 years experience with K-12 construction projects
  GC/CM experience – 8 projects
Will Thomsen, Planning Administrator
  5 years experience with K-12 construction projects
  GC/CM experience – 4 projects
Amy Stenvall, Fiscal Analyst
  10 years experience with K-12 construction projects
  GC/CM experience – 6 projects
John Mannix, Director of Facilities
  27 years experience with K-12 construction projects
  GC/CM experience – 6 projects
  Founding member of Project Review Committee
PROJECT TEAM
3

## Slide 4: PROJECT TEAM
PACIFICA LAW GROUP – LEGAL COUNSEL
Zak Tomlinson, Partner
  Extensive GC/CM Experience
OAC SERVICES – GC/CM ADVISOR
Steve Murakami, Vice President
  23 years experience with K-12 construction projects
  Extensive GC/CM experience leading and assisting Tacoma Public Schools and Lake Washington School District
Dan Chandler, Principal
  40 years of construction experience
  GC/CM experience - 46 GC/CM projects and 20 DB projects
DYKEMAN ARCHITECTS
Tim Jewett, Principal-in-Charge
  23 years of experience with K-12 construction projects
  GC/CM experience – 6 projects
Trish Sherman, Project Manager
  25 years of experience with K-12 construction projects
  GC/CM experience – 4 projects
Michael Stevens, Project Architect
Julia Park, Project Architect
Hannah Melling, Project Support
4

## Slide 5
2020 CAPITAL BOND:
  $240 million bond approved by voters in February 2020
  $105 million for elementary projects
    Increase capacity
    Improve/Expand common support spaces
    Phased replacement of oldest buildings
CHALLENGER ES (CH):
  Original 1987 Structure plus 12 portable classrooms
  Expand & improve common support spaces
HORIZON ES (HO):
  Original 1989 structure plus 7 portable classrooms
  Expand & improve common support spaces
  Add classrooms
TWO PROJECTS – ONE GC/CM
  Sites roughly 1.5 miles apart
  Similar scope & schedule
  Realize efficiencies – procurement, labor, schedule
PROJECT BACKGROUND
5

## Slide 6
CHALLENGER OVERVIEW – EXISTING SITE
6
MUKILTEO SCHOOL
DISTRICT OFFICE
ACES HIGH SCHOOL
EXPLORER MIDDLE SCHOOL

## Slide 7
7
CHALLENGER OVERVIEW – EXISTING SITE
MAIN
ENTRY
PORTABLES
SOFT PLAY
BUS LOOP
PARKING
PICK UP & DROP-OFF
COURTYARD
NEW MUSIC
NEW
GYM
NEW
COVERED
PLAY
NEW KITCHEN
EXTENDED
ADMIN
NEW MULTI-PURPOSE

## Slide 8
HORIZON OVERVIEW – EXISTING SITE
8

## Slide 9
9
HORIZON OVERVIEW – EXISTING SITE
MAIN
ENTRY
PORTABLES
SOFT PLAY
BUS LOOP
PARKING
PICK UP & DROP-OFF
NEW COVERED PLAY
NEW CLASSROOM WING
KITCHEN
MODERNIZATION
NEW
GYM

## Slide 10
This project meets 4 of the 5 criteria.
Implementation of the project involves complex scheduling, phasing or coordination.
The project involves construction at an existing facility that must continue to operate during construction
Involvement of the GC/CM during the design stage is critical to the success of the project
The project encompasses a complex or technical work environment.
The project requires specialized work on a building that has historical significance.
QUALIFYING GC/CM PROJECT
(RCW 39.10.340)
10

## Slide 11: 1. COMPLEX SCHEDULING, PHASING & COORDINATION 2. OCCUPIED SITE
QUALIFYING GC/CM PROJECT - CHALLENGER
  Renovating support spaces used daily by all students
  Construction between buildings/ portables and play areas & next to administrative offices
  Addition where current covered play area is
  Construction entrance shared with ACES HS, staff, buses, parents
  Confined building site with minimal laydown area & staging area
  Maintain fire loop & walking pathways
11

## Slide 12: 1. COMPLEX SCHEDULING, PHASING & COORDINATION 2. OCCUPIED SITE
QUALIFYING GC/CM PROJECT - HORIZON
  Renovating support spaces used daily by all students
  Addition where current covered play area is
  Construction entrance shared with staff, buses, parents
  Confined building site with minimal laydown area & staging area.
  Construction at opposite ends of school
  Maintain fire loop & walking pathways
12

## Slide 13
QUALIFYING GC/CM PROJECT
CHALLENGER & HORIZON
GC/CM brought on during Schematic Design
  Prioritize options from conceptual design to ensure a truly integrated design process.
  Understand market for labor and materials to determine early procurement and early site work and maximize efficiencies of two concurrent projects
GC/CM assistance with initial site and building investigation a significant benefit.
GC/CM input on access, phasing, and safety plans tailored around site restraints.
GC/CM has time to understand school operations and provide input on plans to mitigate noise, vibration, dust, and other issues that may adversely impact the educational environment
3. GC/CM INVOLVEMENT IS CRITICAL TO THE SUCCESS OF THE PROJECT
13

## Slide 14: 4. Complex Work Environment
QUALIFYING GC/CM PROJECT - CHALLENGER
  District property surrounded by homes
  Main entry shared with ACES High School, staff, buses & parents
  Limited parking, Challenger staff use District Office parking. Construction may need to use Explorer Middle School parking across the street
  58% of students at Challenger live in walk area
  Utility work on existing systems for renovations and additions
14

## Slide 15: 4. Complex Work Environment
QUALIFYING GC/CM PROJECT - HORIZON
  Both possible construction access points surrounded by homes
  Apartments along east side of campus where construction happening
  Main entry shared with staff, buses, & parents
  70% of students at Horizon live in walk area
  Utility work on existing systems for renovations and additions
15

## Slide 16
MANAGEMENT PLAN & PROJECT TEAM
Experience
All members of the project team have GC/CM experience.
16
  Controls
  Minimum monthly, high-level team meeting with principal-level involvement.
  Regular school board updates & approvals.
  Procurement
  OAC & Pacifica Law Group guidance.
  Formal selection with 3-step RFP process, and General Conditions & Agreement.

## Slide 17
MANAGEMENT PLAN
17
CHALLENGER - PROJECT SCHEDULE
HORIZON - PROJECT SCHEDULE

## Slide 18
MANAGEMENT PLAN
PROJECT BUDGET
 | Challenger | Horizon
Costs for Professional Services | $616,500 | $1,237,500
Estimated Project Construction Costs | $6,850,000 | $13,750,000
Equipment and Furnishing Costs | $342,500 | $687,500
Contract Administration Costs | $342,500 | 687,500
Contingencies | $685,000 | $1,375,000
Other Related Project Costs (Utility Fees, permits, bid advertising, moving, etc.) | $478,500 | $887,500
Sales Tax | $685.000 | $1,375,000
TOTAL: | $10,000,000 | $20,000,000
FUNDING
  Funding from proceeds of a $240 million capital bond issue passed by voters in February 2020.
  $30 million of the bond processed are designated as the total project cost for these projects.
18

## Slide 19
PROJECT SUMMARY
Traditional delivery method is not desirable
Meets four qualifying criteria
GC/CM will be under contract early in Schematic Design phase
Public body is qualified
Public benefits
19

## Slide 20
QUESTIONS?
20