## Slide 1: Rock Island Dam Powerhouse #2 Draft Tube Gate Cylinder & Hydraulic Power Units Upgrade
Application to use the Progressive D/B Delivery Method
May 29, 2020 Presentation
“To provide sustainable, reliable utility services that enhance the quality
of life in Chelan County.”
Notes: Jim Dugan

## Slide 2: Agenda
Introductions
Chelan County PUD
The Project
Project Budget
Project Schedule
Why Progressive Design-Build
Qualifications
Organization Chart
Summary
Notes: JD

## Slide 3: Introductions
Notes: JD

## Slide 4: The Project Team – Here Today
Chelan County Public Utility District No. 1
John Sagerser, Rock Island EPM Manager
Devin Myers, Rock Island Project Manager
Katie Yount, Internal Legal Counsel
Parametrix
Jim Dugan, D/B Program Advisor
Dan Cody, D/B Procurement & D/B PM/CM Support
Maggie Anderson, Project Controls Specialist
Notes: JD

## Slide 5: The Project Team: Other Team Members
Chelan County Public Utilities District No. 1
Steve Wright, General Manager
Justin Erickson, Managing Director - District Services
Chuck Boss, Construction Manager
Perkins Coie
Graehm Wallace, D/B Legal Advisor
Hydro Design Consultant
Jeff Erwin - Stantec Consulting
Notes: JD

## Slide 6: Chelan County PUD
Notes: John Sagerser

## Slide 7: The District
Chelan County PUD was established in 1936
Second largest, non-federal, publicly owned hydro generation capacity in the U.S.
800 Employees
50,000 Customers
3,000 sq. mile service territory
Approximately 2,000 megawatts of generating capacity
35% of hydropower generated serves county residents, the remainder is sold through contracts and into the energy market.
Three Hydroelectric projects
  Lake Chelan Dam –Built in 1927
  Rock Island Dam – First Powerhouse built in 1933,
                Second Powerhouse built in 1979
  Rocky Reach Dam – Built in 1961
Operate
  Water/wastewater – approx. 5,000 customers
  Fiber & telecom – 13,000 customers
  Parks & recreation – 14 parks along the Columbia River and Lake Chelan
Notes: JS

## Slide 8: The Project
Notes: JS

## Slide 9: Rock Island Dam
Notes: JS

## Slide 10: Rock Island Dam
First Powerhouse built in 1933
First Hydropower project on the Columbia River
Second Powerhouse built in 1979
Last Hydropower project on the Columbia River
Eight (8) original turbine-generator units installed in Powerhouse #2
Turbine-generators and associated Balance of Plant systems have exceeded their 40-year useful life
Upgrading the Draft Tube Gate Cylinders and Hydraulic Power Units will ensure another 40 years of reliable/efficient operation
Upgrades will be phased to minimize disruption to power generation capability
Notes: JS

## Slide 11: Rock Island Dam Draft Tube Gate Cylinder & Hydraulic Power Units Upgrade
Removal of existing cylinders (16 total) and HPUs (8 total) including interconnecting piping (including field piping) and auxiliary systems.
Inspect, analyze and refurbish and/or replace cylinders and HPUs
Shop testing of hydraulic cylinders and HPU
Provide all electrical power & controls
Provide new environmentally friendly hydraulic fluid
Replace interconnecting piping (including field piping) and auxiliary systems.
Installation of cylinders, HPUs including piping and auxiliary systems
Provide labor, supervision, tooling, cranes and scaffolding for removal and installation
Assist in startup and commissioning of refurbished system
Scheduling to be coordinated with District generator outages
Notes: Devin Myers

## Slide 12
Notes: DM

## Slide 13
Notes: DM

## Slide 14: Rock Island Dam Powerhouse #2 Draft Tube Gate Cylinder & Hydraulic Power Units Upgrade Project Budget
Category | Budget
Costs for Professional Services (A/E, Legal, etc.) | $ 200,000
Cylinder Manufacturing/Refurbishment | $ 2,250,000
HPU Manufacturing/Refurbishment | $ 1,800,000
Auxiliary Systems and Piping | $ 1,250,000
Installation construction costs (Inc. Manufacturing and Install) | $ 1,400,000
District Administration and Project Management | $ 145,000
Total | $ 7,045,000
Note: All design and construction costs identified above include 8.3% sales tax, 5% owners project contingency and a combined 20% contingency for design, construction, escalation and inflation
Notes: DM

## Slide 15: Project Funding
  Overall project scope, schedule and budget were presented as part of the Powerhouse Two Rehabilitation Program to District Board of Commissioners in November 2017
  Approved 2018 capital funds associated with the project
  District currently plans to fund project with cash reserves until 2022
  District has not issued bonds for capital projects since 2009
  Average capital expenditure of $44M between 2010 and 2017 using cash reserves
  District’s current bond rating is AA+/Stable, one of the top five public utilities
  Ability to fund project after 2022 using external debt is high
Notes: DM

## Slide 16: Rock Island Dam Powerhouse #2 Draft Tube Gate Cylinder & Hydraulic Power Units Upgrade D/B Schedule
Project Schedule | Estimated Date
PRC Presentation | May 29,2020
Publication of RFQ for Design/Build Services | June 2, 2020
Project Information Meeting (Date subject to change.) | June 11, 2020
RFQ Submittal Deadline | July 9, 2020
Open & Review/Score Submittals Received | July 9-16, 2020
Identify Finalists & Issue RFP & Proprietary Meeting Notifications | July 17, 2020
Proprietary Meeting #1 | August 26 - September 2, 2020
Proprietary Meeting #2 (if required) | September 18-21, 2020
RFP Submittal Deadline (Proposals & Cost Factors) | September 16-23, 2020
Open & Review Proposals (Cost Factors not reviewed) | October 19-23, 2020
Open Cost Factors & Score Proposals | October 24, 2020
Design/Builder Interviews | October 29-November 4, 2020
Notify Design/Builders of Scoring and Most-Qualified Design/Builder | November 17, 2020
Notes: DM

## Slide 17: Rock Island Dam Powerhouse #2 Draft Tube Gate Cylinder & Hydraulic Power Units Upgrade D/B Schedule
Project Schedule | Estimated Date
Design/Build Contract Negotiation | November 25-December 23, 2020
Execute Design/Build Agreement with Preconstruction Phase | December 2020
Preconstruction Phase/GMP Negotiation | December 2020-January 2021
GMP Amendment Executed | February 2021
Manufacturing – First Unit and Unit Common | March 2021 – July 2021
Site Set-up and Mobilization | July 2021 – September 2021
Construction Phase | September 2021 – January 2029
Notes: DM

## Slide 18: Rock Island Dam Powerhouse #2 Draft Tube Gate Cylinder & Hydraulic Power Units Upgrade Project Development Schedules
Critical Phasing
Notes: DM

## Slide 19: Rock Island Dam Powerhouse #2 Draft Tube Gate Cylinder & Hydraulic Power Units Upgrade Project Development Schedules
Critical Phasing
Notes: DM

## Slide 20: Why D/B Delivery Method for Rock Island Dam Powerhouse #2 Draft Tube Gate Cylinder & Hydraulic Power Units Upgrade Project
Notes: DM

## Slide 21: RCW 39.10 D/B Statutory Compliance
(5.1) If the construction activities are highly specialized and a D/B approach is critical in developing the construction methodology
  Rock Island Powerhouse 2 is part of the Bulk Electrical System which is considered critical infrastructure.
  “Bulb” turbine-generator rare in the U.S.
  Powerhouse 2 is an operating power plant. Phased construction required to minimize operational impacts on power generation
  Limited access for removal and reinstallation
  Work to refurbish DTG cylinders and HPUs is highly labor intensive, specialized and technical in nature
  The Design Builder, performing the work must have the ability to design and manufacture as well as remove and reinstall the new components
  Very tight clearances/tolerances required between operational and stationary components
(5.2) If the project provides opportunity for greater innovation and efficiencies between the designer and builder
  The cylinders and HPUs requirements for this project can be designed in numerous ways
  Proprietary design solution can be leveraged to achieve the technical requirements for this project
  Design may vary based on specific condition and needs of each unit
  Owner does not have expertise to specify options for improvement to existing systems
(5.3) If significant savings in project delivery time would be realized
  The refurbishment of the cylinders and HPUs will be done during unit outage.
  It will be imperative that the contractor is involved in scheduling and phasing of the work.
  Scheduling and installation innovation can reduce the outage time required
Notes: DM

## Slide 22: Public Body Qualifications
Notes: JS

## Slide 23: CCPUD Leadership Team
CCPUD has extensive construction experience including projects of similar scope and complexity
  Long history of projects delivered using Design-Bid-Build or Negotiated Contract.
  Long track record of building projects on-time and within budget.
CCPUD is relatively new to the Design Build method of project delivery
  CCPUD is currently using Progressive Design-Build for RI PH2 Generator and Turbine Rehabilitation
  CCPUD is currently using GC/CM for two facilities projects.
CCPUD team members have attended the upcoming AGC Design-Build Workshop
CCPUD team members have attended and are registered to attend the upcoming DBIA Certification Workshop
Parametrix: Dan Cody D/B PM Support and Jim Dugan Internal D/B Advisor
Graehm Wallace, (Perkins Coie): External D/B Legal Counsel
CCPUD satisfies the public body qualifications by staff augmentation with consultants.
Notes: JS

## Slide 24: Rock Island Dam Powerhouse #2 – Draft Tube Gate Cylinder & Hydraulic Power Units Upgrade Project Organizational Chart

## Slide 25: Rock Island Dam Powerhouse #2 – Draft Tube Gate Cylinder & Hydraulic Power Units Upgrade Project Organizational Chart
Project Team Member | Draft Tube Gate HPU and Cylinder Upgrade Project |  | Generator Main Lead Project |  | Other Duties
 | Procurement & Design | Construction | Procurement & Design | Construction | 
District Project Team |  |  |  |  | 
John Sagerser – Program Manager | 10% | 10% | 10% | 10% | 80%
Devin Myers – Project Manager | 15% | 20% | 15% | 20% | 60%
Jeff Erwin (Stantec) – Project Engineer | 50% | 50% | 0% | 0% | 50%
Chuck Boss – Construction Manager | 15% | 35% | 15% | 35% | 30%
Katie Yount – Internal Legal Counsel | As Needed | As Needed | As Needed | As Needed | 
Consultant Project Team |  |  |  |  | 
Jim Dugan – D/B Consultant | 25% | 5% | 25% | 5% | 
Dan Cody – D/B Procurement Mgr. | 25% | 0% | 25% | 0% | 
Graham Wallace – External Legal Counsel | As Needed | As Needed | As Needed | As Needed | 
Vik Negi (Stantec) – External Engineering Consultant | As Needed | As Needed | As Needed | As Needed | 
Chelan PUD Organizational Structure:
The District is currently in the process of rehabilitating powerhouse two at Rock Island Dam. This project is a balance of plant project that will be executed as part of the full powerhouse rehabilitation project. Several of the project team members are participating in two DB projects being presented today. Through the DB procurement process, we will secure contracts with experienced teams of Contractors that will need limited support and oversight from the project team during the execution phase of this project. The District does, however have a deep bench including internal personnel in addition to Service Agreements for engineering and project administrative personnel if needed.
Notes: JS

## Slide 26
Project Team D/B Experience
Notes: JS

## Slide 27
Name | Experience
John Sagerser Rock Island EPM Manager Chelan County PUD | 28 yrs. Electrical Engineering/Project Management Experience 17 yrs. Hydro Engineering/Project Management Experience Project Manager for Lake Chelan Hydro Modernization ($35M 2006 to 2010) Project Manager for Rock Island Powerhouse 1 Rehabilitation (2015 to 2018)
Devin Myers Rock Island Project Manager Chelan County PUD | 17 yrs. Hydroelectric Industry Maintenance Planning/Project Management RI PH2 Draft Tube Gate Refurbishment($4.4M 2016 to 2019) RI PH2 Storage Building (Initiation through Bidding) ($3.4M 2016-2017) RI PH2 Oil Handling System($650K 2016 to 2018)
Chuck Boss Construction Manager Chelan County PUD | 20 yrs. Industrial Engineering/Construction Management Experience 12 yrs. Hydro Construction Management/Quality Control Experience Construction Manager Rock Island Powerhouse 1 Rehabilitation QA/QC Representative Rock Island Powerhouse 1 Rehabilitation Construction Manager Rock Island Denil Installation/Removal
Jim Dugan D/B Program Advisor Parametrix | 40 yrs. Program/Project Management Projects: TPS – Boze Elementary School; TPS Hunt Middle School; Willapa Elementary School Gym; Multiple large D/B projects worldwide with The Austin Company Project Review Committee Member: 3 Year Term Ends June 2019
Notes: JS

## Slide 28
Name | Experience
Dan Cody D/B Procurement and PM Support Parametrix | 30 yrs. Of Design & PM/CM 4 D/B Projects: South Puget Sound Community College – Lacey Campus; Building #1; Tacoma Public Schools – Boze Elementary School; Tacoma Public Schools – Hunt Middle School; Willapa Elementary School Gym
Graehm Wallace Outside Legal Counsel Perkins Coie | Graehm has prepared Design-Build contract documents under RCW 39.10 for the Washington State School Directors Association, the Tacoma School District, and the Willapa Valley School District as well as Design-Build contract documents for dozens of private projects. Graehm has over twenty-two years legal counsel experience working in all areas of construction and has provided legal assistance to over 100 Washington public entities. His work has covered all aspects of contract drafting and negotiating. This includes preconstruction, architectural, engineering, construction-management, GC/CM, Design-Build and bidding. Graehm has also provided legal advice during construction, claim prosecution and defense work.
Notes: JS

## Slide 29: Summary
Project is funded with the appropriate budgets
Projects meet qualifying RCW criteria
Project Management Plan is developed and has clear and logical lines of authority
Project team has the necessary experience
Project team has the capacity
Project team is prepared and ready to proceed
Notes: JD

## Slide 30: Thank you
Notes: All