## Slide 1: Client Workshop April 18, 2017
Notes: Please mention:
Restroom locations
Emergency Exits
There will be a break in the morning, boxed lunches, and an afternoon break

## Slide 2: Morning Agenda
7:45 am Registration\Networking
8:30 am Welcome
8:45 am Biennium Scheduling
9:05 am Project Delivery Methods Panel
10:30 am Choosing Project Delivery Methods
- Table Top Exercise
11:00 am Roles & Responsibilities
11:30 am Public Works Request (PWR) Form
11:40 am Inter-Agency Agreements

## Slide 3: Afternoon Agenda
1:00 pm Improving Project Work Flow
- Table Top Discussion
2:00 pm Governor’s Diversity Initiative
2:45 pm What is Public Works?
3:45 pm Closing Remarks
4:00 pm Workshop Closes

## Slide 4: Welcome
Janet Jansen, Project Manager
Engineering & Architectural Services
Department of Enterprise Services
(360) 407-8265

## Slide 5: Facility Professional Services Division

## Slide 6: Biennium Scheduling Best Practices
Marty Mattes
Director of Facilities & Operation
Bates Technical College
(253) 680-7156
See Minor Works Presentation

## Slide 7: Biennium Scheduling Best Practices
Thank you!
Marty Mattes
Director of Facilities & Operation
Bates Technical College
mmattes@bates.ctc.edu
(253) 680-7156

## Slide 8: Project Delivery Methods
Design-Bid-Build
Small Works Roster
Job Order Contracting
General Contractor\Construction Manager
Design-Build
Panel Questions & Answers

## Slide 9: Project Delivery Methods
Design-Bid-Build
Jeff Gonzalez, Project Manager
Engineering & Architectural Services

## Slide 10: Design-Bid-Build
Most common delivery method for public works projects
Linear process – Project is fully designed prior to bidding the construction contract
Services are segregated into separate contracts between owner/architect and owner/contractor

## Slide 11: Design-Bid-Build
Contactor competition is based on low bidder
Construction costs are “known” at the time bids are received
Construction alternates are then decided based on bids and budget

## Slide 12: Design-Bid-Build
Separates design and construction, used for projects of any size
Phases:
Predesign
Design
Construction
Contractor hired
Awarded to responsible bidder with lowest responsive bid
Construction cost established
Source: JLARC analysis of public works contracting procedures, Sunset Review, Dec. 2012.
Architect/ Engineer hired
Invitation to bid

## Slide 13: Design-Bid-Build
Owner
General Contractor
Sub-Contractors
Sub-Consultants
Architect / Designer
Contractor Selection Process Here

## Slide 14: Benefits of Design-Bid-Build
Traditional project delivery method that is familiar
Owner has control over the design process
Architect works directly for the owner
Good alternative when construction risks are relatively low and pricing is the most significant factor
Contractor selection is non-subjective, simple, and quick

## Slide 15: Considerations/Challenges of Design-Bid-Build
Not an integrated delivery method – Contractor does not have early involvement during design
Does not easily allow for contractor input as it relates to the design
Firm pricing isn’t known until the time bids are received
Contractor selection is based solely on price, not performance

## Slide 16: Considerations/Challenges of Design-Bid-Build
  Owner warrants the sufficiency of the plans and specs to the contractor
  Owner liable for any mistakes between plans, specs, and performance
  Project is constructed per plans and specifications
  Plans and specifications must be clear and without ambiguity

## Slide 17: Design-Bid-Build
Thank you!
Jeff Gonzalez, Project Manager
Engineering & Architectural Services
Jeff.Gonzalez@des.wa.gov
(360) 407-7942

## Slide 18
Small Works Roster
Jonathan Martin, Project Manager
Engineering & Architectural Services
Project Delivery Methods

## Slide 19: Small Works Roster
Small works roster contract procedures RCW 39.04.155
1981 - Small Works procedures began modestly, with a limit of $25,000. Only four specific state agencies; General Administration, Fisheries, Game, and Parks and Recreation Departments were authorized to the SWR.
1991 – Limit raised to $100,000
2000 – Limit raised to $200,000
2009 – Limit raised to $300,000
Notes: Brief History of Washington State’s Small Works Process

## Slide 20: Small Works Roster
The Small Works Roster (SWR) is a pool of pre-approved contractors licensed in the State of Washington who have applied for and been placed on the roster.
The SWR can be used for projects under $300,000 Total Construction Cost.
  Makes it easier for contractors to compete for public works projects
  Helps reduce the cost of bidding small projects
  Faster pace procurement process
  Known bidder pool
Notes: Brief History of Washington State’s Small Works Process

## Slide 21: Small Works Roster
Is project under $300K
PM assembles Bid Package
  Scope Summary
  Front End Documents
  Drawings
OR
PM may use On-call or from A/E Reference File
PM puts date timelines together with Facility
  Date to send notification
  Deadline for response of interest
  Date of walkthrough
  Deadline and location for bid submittal
PM obtains project number
PM fills out the SWR Notification Worksheet
Run the Roster
  Tweak Contractor types and specialties to obtain a usable list
  Minimum of at least 5 firms
Print the roster
Complete the notification page and proof for spelling, grammar and readability
SEND
Print copy of the notification email showing date and time and addressees for contract file
Respond to requests for Bid Documents, note firms on Roster
Following Walkthrough place copy of sign-in form in contract file
Prepare Bid Summary Sheet
Following Bidding Deadline – process as per usual procedure
Forward to Contracts office

## Slide 22: Small Works Roster
Thank you!
Jonathan Martin, Project Manager
Engineering & Architectural Services
Jonathan.Martin@des.wa.gov
(360) 407-9353

## Slide 23
Job Order Contracting (JOC)
Dennis Flynn, Project Manager
Engineering & Architectural Services
Project Delivery Methods

## Slide 24: Job Order Contracting
A competitively bid fixed-price contract for multiple construction projects delivered on a work order basis.
Unit prices from R.S. Means for establishing lump-sum fixed prices for work orders.
Contractor provides coefficient that is applied to line items from R.S. Means.
Contracts can be awarded for up to three years @ $6M per year.

## Slide 25: JOC Projects
Projects that have a short timeline to complete
Projects that can have an abbreviated design
Projects that would benefit from early Contractor involvement
Multi-discipline projects
Bundled projects
Projects under $350,000

## Slide 26: Job Order Process

## Slide 27: Benefits of Job Order Contracting
Joint scoping and incidental design decreasing design cost and reduces change orders
Contractor works with Owner to make project work within budget
Can Reduce total project time by 10%-20%

## Slide 28: JOC Considerations
JOC may not be the preferred delivery method if:
  Detailed design is required
  Intensive CA is required
  Competitive bids are preferential

## Slide 29: JOC Contractors
NW Region- Saybr
SW Region- Centennial (at capacity)
Western WA- Forma (at capacity)
Eastern WA- Burton (at capacity)
Statewide- Burton (at capacity)
Statewide- Centennial - (contract pending)
New Contracts for Statewide and SW Region will bid this spring

## Slide 30: Job Order Contracting
Thank you!
Dennis Flynn, Project Manager
Engineering & Architectural Services
Dennis.Flynn@des.wa.gov
(360) 407-7934

## Slide 31: Project Delivery Comparison
Project Delivery Options
Option | $ Limits | When to Use | Advantages | Disadvantages | RCW Ref.
Design-Bid-Build | — | When other options don’t make sense | Competition that most contractors understand | Contractor not a participant in design | 39.04
Job Order Contract (JOC) | $350k (w/COs) | Need it fast Simple with few trades | Convenient | Pay for convenience | 39.10. 420-460
Small Works Roster | $300k (w/COs) | Small, simple projects | Less design Shorter time | Low bidder interest can result in few or no bids | 39.04. 155
Notes: Brief History of Washington State’s Small Works Process

## Slide 32: Relative Schedule Comparisons Between Contracting Methods
Assume: $200,000 Construction Cost + Non-Elective Change Orders/Basic Design Requirements/120 Day Construction Duration

## Slide 33: Relative Total Project Cost Comparisons Between Contracting Methods
Assume: $200,000 Construction Cost + Non-Elective Change Orders/Basic Design Requirements/120 Day Construction Duration

## Slide 34: Project Delivery Methods
General Contractor\ Construction Manager
Christopher Gizzi, Project Manager
Engineering & Architectural Services

## Slide 35: General Contractor\ Construction Manager
GC/CM – GCCM
General Contractor Construction Manager
CM/GC – CMGC
Construction manager General Contractor
CM/R – CMR - CMAR
Construction Manager at Risk

## Slide 36: General Contractor\ Construction Manager
The GC/CM project delivery method allows an owner to engage a construction manager during the design phase to provide constructability input.
The GC/CM is generally selected on the basis of qualifications, past experience, and a competitively bid fee factor or a best-value basis.
During the design phase the construction manager provides input regarding scheduling, pricing, phasing, and other input that helps an owner design a more constructible project.
At approximately 90% design completion the owner and the construction manager negotiate a Maximum Allowable Construction Cost (MACC) and Total Construction Cost (TCC) for the construction of the project based on the defined scope and schedule.
If this price is acceptable to both parties, they execute a contract for construction services.

## Slide 37: GC/CM Delivery Method
With the GC/CM project delivery method, the design firm and construction firm are both contracted to the owner.

## Slide 38: Method Schedule Comparison
Design Bid Build
GC/CM
Images Mortenson Co.

## Slide 39: Delivery Method Comparison
Project Component | Design-Bid-Build | General Contractor / Construction Manager (GC/CM) | Design-Build
Architect/Engineer Selection Timing | Select at Beginning of Design Phase | Select at Beginning of Design Phase | Select as part of contractor team after facility programming.
Competition | Qualifications based with negotiated fee. | Qualifications based with negotiated fee. | Qualifications and fee-based as part of contractor team.
Role | Fully design project in advance of construction working closely with owner. | Fully design project in advance of construction working closely with owner and selected GCCM. | Design project under direction of contractor to meet programming requirements. Part of design may extend into construction.
Contractor Selection Timing | Select at completion of design | Select at 30% design Enter Construction contract at 90% design | Select as part of AE team after facility programming
Competition | Low Bidder | Combination of qualification s& sealed bid fee. Owner and GC/CM negotiate MACC at 90% design, if parties cannot agree on MACC, owner may either put the project out for bids or negotiate next highest ranked GC/CM. | Qualifications and fee-based as part of team with A/E.
Role | Construct project per plans and specifications. Select and manage subcontractors. | Assist Owner & A/E in design phase with independent cost estimates, constructability reviews, and cost saving suggestions. Package subcontractor work for sealed, publicly opened bids per A/E plans &specs. Manage subcontractors & self-perform work. | Lead A/E in design project per programming requirements. Construct project per design-build team construction documents, Select & manage subcontractors
Subcontractor Selection and Competition | By contractor using contractor selection criteria. | Low bidder on sealed, publicly opened bids managed by Contractor. | By Contractor using Contractor selection criteria.
Project Price | Negotiated A/E Fee Lump Sum Construction bid Approved Change Orders | Negotiated A/E Fee GCCM Sealed Bid Fees for General Cond.’s Lump Sum Subcontractor Construction bids Approved Change Orders | Programming Costs Lump Sum DB Construction Bid Approved Change Orders

## Slide 40: RCW 39.10.340
How does GC/CM Meet Requirements for Competition?
Under GC/CM, a public agency advertises a Request for Proposals and selects a general contractor based on qualifications and price to provide pre-construction design assistance and construction management.
At about 90% completion of architect’s documents, the Owner and GC/CM jointly agree to a Negotiated Maximum Allowable Construction Cost (MACC) and Total Construction Cost (TCC).
Actual construction work is then competitively bid to sub-contractors in the same manner as traditional design-bid-build process by issuing solicitations for the work, receiving sealed bids and awarding based on low bid.
Project Costs exceeding the Negotiated MACC are the responsibility of the GC/CM. Project savings are returned to the owner.
State requirements (e.g. Diversity, Prevailing Wage, Retainage, etc,) are included in the GC/CM contracts and passed down to subcontractors.

## Slide 41: Advantages to GC/CM
GC/CM can provide input on phasing and sequencing need for projects that must remain operational during construction.
Allows ‘fast track’ construction to start while detailing structures, interiors, and systems by awarding site work, foundations, and long lead items (such as precast concrete and major equipment contracts – Note: contingent on permitting agency cooperation)

## Slide 42: Advantages to GC/CM
GC/CM Is able to provide constructability reviews and independent cost estimates throughout the design phase of the project.
GC/CM aids in evaluating system options and obtaining real time cost estimates.
Image Walsh Construction

## Slide 43: Advantages to GC/CM
GC/CM has valuable experience on cost savings that could be incorporated into the design.
Provides constructor’s input into systems, labor and materials availability, work and trade sequencing, and construction methodologies that can reduce design and construction time and costs.
Image
NAC Architecture

## Slide 44: Advantages to GC/CM
GC/CM can become familiar with the intricacies and challenges of a complex project during design and carry that knowledge into construction.
Challenges the entire project team to stay within budget by allowing full and frank discussions of the cost and schedule implications of various design solutions, thereby allowing the owner to make informed cost-benefit tradeoff decisions.

## Slide 45: Advantages to GC/CM
Constructor well qualified to perform the work and not just the low bidder.
Provides the construction team the opportunity to jointly develop an aesthetically pleasing operational , functional, space-efficient building design utilizing low maintenance and reduced life cycle systems.

## Slide 46: Potential Challenges
Determining a fair and reasonable GMP for the project in relation to the AE’s design vision, the owner’s requirements, the public entity’s expectations and the GC/CM’s proposal.
Determining the GC/CM’s risk contingency percentage for the project.
Determining when the GC/CM will give a Total Construction Cost for the project.
Determining the number of bid packages and the level of detail required for each phase of the design (impacts AE Fees), when the TCC will be confirmed, and the amount (%) necessary for the GC/CM’s estimating contingencies and escalation factors.
Understanding the difference in how construction cost is categorized, i.e. cost of the work, GC/CM Fee, general conditions, negotiated support services, risk contingency, construction ‘contingency’, and management reserve.
Determining how planning and permit timelines align with design and construction milestones.

## Slide 47: Potential Challenges

## Slide 48: Owner Challenges
Managing the disruption of construction activities on an occupied campus including traffic impacts due to hauling routes and material deliveries,
Dedicating personnel to the design and construction process. Representatives need the authority to make final decisions and garner consensus from various agency hierarchies. This is a vital role in the process. The agency will produce benefit from the process in direct relation to their ability to make timely decisions, understand the particular needs and requirements of the project, stay current with project issues and generally drive the process.
Working with local building/planning departments to give advance notice of intention, clear regulatory hurdles, and pre-construct infrastructure that could impact project delivery timelines.
Managing cash flow and payments to consultants, testing agencies, contractors, and jurisdictions.
Planning the purchase, delivery, storage, and installation of furnishings & equipment.
Maintaining perspective, understand the sausage-making aspect of the work, and having fun!

## Slide 49: Owner Challenges

## Slide 50: General Contractor\ Construction Manager
Thank you!
Christopher Gizzi, Project Manager
Engineering & Architectural Services
Christopher.Gizzi@des.wa.gov
(360) 407-9304

## Slide 51: Project Delivery Methods
Design-Build
Robynne Parkinson, Attorney
Thaxton Parkinson, PLLC
rparkinson@rtp-law.com
(206) 909-5290
See Design-Build Presentation

## Slide 52: Design-Build
Thank you!
Robynne Parkinson, Attorney
Thaxton Parkinson, PLLC
rparkinson@rtp-law.com
(206) 909-5290

## Slide 53: Project Delivery Methods
Panel
Questions?

## Slide 54
~ Break Time ~

## Slide 55: Choosing Project Delivery Methods?
~ Table Top Exercise ~
Nancy Deakins, Asst Prog Manager
Engineering & Architectural Services
Nancy.Deakins@des.wa.gov
(360) 407-9333

## Slide 56: Roles & Responsibilities
Bob Bourg, Manager
Claims & Disputes
Bob.Bourg@des.wa.gov
(360) 407-9370
See Roles & Responsibilities Document

## Slide 57: Roles & Responsibilities
Thank you!
Bob Bourg, Manager
Claims & Disputes
Bob.Bourg@des.wa.gov
(360) 407-9370

## Slide 58: Public Works Request Form
Curtis Pate, Contract Specialist
Contracts Section

## Slide 59: Public Works Request Form

## Slide 60: Public Works Request Form

## Slide 61: Public Works Request Form

## Slide 62: Public Works Request Form

## Slide 63: ‘Signing’ the PWR

## Slide 64: The Form – MS Excel

## Slide 65: Public Works Request Form
State Agency and Educational Facilities can find the form at: http://des.wa.gov/services/facilities-leasing/public-works-design-construction/state-agencies-and-educational-facilities
Forms/Reference documents can be found at: http://des.wa.gov/services/facilities-leasing/public-works-design-construction/formsreference-documents
Email the form to:
eas-pwr@des.wa.gov

## Slide 66
Thank you!
Curtis Pate, Contract Specialist
Contracts Section
Curtis.Pate@des.wa.gov
(360) 407-7913
Public Works Request Form

## Slide 67: Inter-Agency Agreements
Janet Jansen, Program Manager
Engineering & Architecture Services
Janet.Jansen@des.wa.gov
(360) 407-8265

## Slide 68
Thank you!
Janet Jansen, Program Manager
Engineering & Architecture Services
Janet.Jansen@des.wa.gov
(360) 407-8265
Inter-Agency Agreements

## Slide 69: Thank you
~ Lunch Time ~
Switch to Deck 2