## Sheet1
Generous County Washington
General Contractor/Construction Manager (GC/CM) and Design-Build (D-B) Contracting
Project Approval Flow Chart
STEP 1 |  |  |  | STEP 2 | STEP 3
PM uses internal written guidelines and staff review process to determine whether GC/CM or DB is appropriate * |  |  | PM prepares documentation (schedule, cost analysis and rationale) for using GC/CM or D-B. |  | PM presents documentation to CA.
STEP 4 |  |  |  | STEP 5 | STEP 6
CA reviews documentation; requests clarifications; and makes determination to whether to proceed further. |  |  | CA, PM and experienced staff work with A/E and other consultants to test whether documentation supports use of GC/CM or D-B. |  | EXEC receives documentation; determines whether to proceed further.
STEP 7 |  |  |  | STEP 8 | STEP 9
EXEC authorizes presentation to EO for consideration of GC/CM or D-B. |  |  | EO makes initial determination to use GC/Cm or D-B; authorizes public comment using agency's PCP. |  | PM, CA and A/E advertise and hold public comment meetings; address public comments.
STEP 10 |  |  |  | STEP 11 | STEP 12
PM, CA, and A/E modify project based on public comment (as appropriate). |  |  |  | PM and CA present modified project to EXEC for authorization to present to EO | PM and CA present modified project to EO for approval .
STEP 13 |  |  |  | STEP 14
EO, based on second review and recommendations of advisors, authorizes project and use of GC/CM or D-B. |  |  |  | PM and CA provide project data to state (CPARB) for tracking project
Key:
EO | Elected officials | (legislative body)
PCP | Public comment process
EXEC | Public agency's highest executive position
A/E | Architectural/Engineering consultants
CA | Construction Section/Division's management authority
PM | Project managers
* See attached project guidelines (criteria sheet)