## Sheet1
Generous County's Typical Management Plan for GC/CM or D-B Projects
Note: A specific Project Management Plan (organization chart) will be developed and published for each project. This plan will be prepared during the project authorization phase and will identify all key employees and consultants (and their expertise) who will be assigned to the project.
Executive-Legislative Oversight
Construction Department (Management Oversight Authority)
| Procurement |  |  | Generous County's Project Manager | Legal Counsel
Contractor's Project Manager
Experience, Roles, Responsibilities
Executive-Legislative Oversight |  | Reviews and approves all projects individually, ensures that guidelines for type of project is met; requires monthly written progress reports; makes quarterly presentations to legislative authority (county council); etc
Construction Department |  | Ensures that all criteria for internal selection of & documentation for alternative project contracting procedure are met; assigns staff with appropriate experience full time to project or hires a qualified consultant to augment or run the project; ensures that all reports to the county executive are submitted as required; ensures that data is submitted to the state (CPARB) as required.
Project Manager |  | Experienced with the type and size of project, as well as the alternative contracting methodology. (Typically a staff member, but also may be under contract. If under contract, Construction Department or Management Oversight Authority will assign staff experienced in managing projects of similar types and sizes and project manager will mentor them in the alternative contracting procedure. Experienced legal counsel and procurement staff will advise project manager.
Legal Counsel |  | Legal counsel experienced in developing construction documents and negotiating construction contracts for at least one project using the same alternative contracting procedure will be assigned to assist the PM and Procurement. Counsel (on-staff or under contract) will also be available during negotiations and the finalization of construction documents.
Procurement |  | Procurement staff experienced in developing construction documents and negotiating construction contracts for at least one other project using the same alternative contracting procedure will be assigned.