## Slide 1: Boundary Generator Unit Overhaul Project
For Generator Units 51, 52 & 54
October 10th 2017

## Slide 2: Introductions
Mike Haynes, Generation Officer
Wanda Schulze, Capital Program Manager
Josh Jackson, Project Manager
Aleanna Kondelis, Contracts Manager
Mike Nordin, Construction Manager
Robynne Parkinson, DB Advisor
Rebecca Keith, Law Department
Dan Kirschbaum, Mechanical Engineering Manager
Faz Kasraie, Electrical Engineering Manager
Notes: Josh

## Slide 3: Project Org Chart
Notes: Josh
Engineers will be 100% during construction phase
PM Boundary 100%, doing transformers
Show GO&E org chart

## Slide 4: Boundary Dam Overview
On the Pend Oreille River, in the NE corner of Washington State
In service since 1967
6 generating units (Units 51-56)
  55 & 56 overhauled in 2012 and 2014
  53 overhauled through emergency in 2013
Over 50% of SCL’s generation capacity
This project is an overhaul of units 51, 52, & 54
Notes: Josh

## Slide 5: Project Location
Notes: Josh

## Slide 6: Site Overview
Notes: Josh

## Slide 7: Powerhouse Section View

## Slide 8: Generator Section View

## Slide 9: powerhouse floor Units 51-54

## Slide 10: Generator Shaft Removal
Notes: 90 tons
33”

## Slide 11: Generator Stator Windings

## Slide 12: Windings Were Switched out For Bars

## Slide 13: Project Schedule
Activity | Projected Date
RFQ Issued | October 13, 2017
SOQs Due | November 3, 2017
Short-List | November 9, 2017
RFP Issued | November 13, 2017
Proprietary Mtg. One, Two | January 12 & 26, 2018
Proposals Due | February 9, 2018
Selection of Design-Builder | February 28, 2018
Negotiations/Contract Execution | March 2018
Design Phase including validation periods | March 2018 – March 2019
Manufacturing (on-going) | September 2018 – March 2021
Construction Phase | July 2019 – April 2022
Generator (U51) Outage | July 2019 – April 2020
Generator (U54) Outage | July 2020 – April 2021
Generator (U52) Outage | July 2021 – April 2022
Notes: Josh

## Slide 14: Contract Schedule Overview
Notes: Josh

## Slide 15: Project Budget
Costs for Professional Services (A/E, Legal etc.) $1,100K
Estimated project construction costs with contingences: $30,300K
Equipment and furnishing costs (included in above)
Off-site costs (off-site manufacturing is included in above)
Contract administration costs (Owner, PM, CM etc.) $7,500K
Contingencies (15%) $4,500K
Other related project costs (Owner performed work) $19,000K
Sales Tax (7.6% Pend Oreille County) $3,000K
Total $65,400K
Notes: Wanda

## Slide 16: Management Controls
Project Management Framework
  Charter
  Executive sponsorship
  Ongoing Risk Analysis
Construction Management
  Construction controls
Finance Controls
  City Light financial governance policy
Notes: Wanda

## Slide 17: DESIGN-BUILD IS CRUCIAL FOR THIS PROJECT
RCW 39.10.300
  Construction activities are highly specialized and a design-build approach is critical, or
  Opportunity for greater innovation or efficiencies between the designer and the builder, or
  Significant savings in project delivery
Significant Public Benefit
  Time savings = income to SCL
  Full warranty on equipment
  Reduced operations and maintenance
Notes: Robynne

## Slide 18: SCL team is fully Qualified
Two prior similar projects with the same personnel
    Boundary Units 55 & 56
    Diablo Powerhouse Units 31 & 32 (in construction)*
Certifications
    DBIA
    PMP
    PE
    CCM
Design Build Advisor
Subject Matter Experts
Notes: Robynne

## Slide 19: City Org chart - Broad
Mayor/Council
Finance Department Head
Contracting Director
Power Generation Officer
SCL General Manager & CEO
Power Generation Program Manager
Contracting Manager
Law
Contracts & Utilities Section
Notes: Aleanna

## Slide 20: Question #1
Q1. How is the overlap in workload on all Units supported by the proposed team? Are there different teams working on Units #55 and #56?
Work on 55 & 56 will be complete before award
Most design will be done in 1st year of contract
Construction work under this project will be performed in 3 separate outages
Only 1 generator will be out of service at a time
Each outage includes a design validation phase for that generator

## Slide 21: Question #2
Q2. Please explain (1) How your proposed staffing and availability will support the proposed workload, (2) Who in fact is the single person responsible for this program and (3) Why no one on the organization chart is allocated as available 100%?
Only 1 generator out of service at a time
Workload will be steady throughout the project
Lessons learned from past overhauls applied to staffing plan
Mike Haynes, Generation Officer, is single person responsible
Org chart shows department heads, all have staff dedicated 100%
PM is also responsible for a related, coordinated project at Boundary

## Slide 22: Question #3
Q3. Please describe your lessons learned in the two (2) prior Design-Build Hydroelectric Generator rehabs and how those lessons learned have translated into doing the next three Hydroelectric Generator rehabs differently?
Dedicated construction management
Self-sufficiency as a project goal and procurement criteria
Selection criteria emphasize project management and execution
Design validation at the project and unit levels
Minimize personnel changes and mitigate impact

## Slide 23: Question #4
Q4. Please provide a copy of the Project Charter that you have described as completed for this program of projects.
The project charter was provided with response to questions.

## Slide 24: Question #5
Q5. Will this project be covered under a CWA (Community Workforce Agreement)?
No, the City’s CWA does not cover projects in remote locations such as Boundary.

## Slide 25: Question #6
Q6. Will this project require a WMBE Inclusion Plan?
Yes, part of the proposal process will include a social equity and inclusion plan and approach including a proposed aspirational goal to include women, minority, and small business opportunities.