## Slide 1
North Mason Regional Fire Authority
Headquarters Fire Station
Project Review Committee | Project Approval Process
March 26, 2020

## Slide 2
ATTACHMENT A – NORTH MASON REGIONAL FIRE AUTHORITY HQ FIRE STATION
PROJECT ORGANIZATIONAL CHART
D-B RFQ/RFP - 10%
Design - 10%
Construction - 15%
Aron Aston Estimator Hill International, Inc.
D-B RFQ/RFP - 10%
Design - 10%
Construction - 15%
Mamie Kamada Document Controls Specialist Hill International, Inc.
D-B RFQ/RFP - 10%
Design - 10%
Construction - 15%
D-B RFQ/RFP - 50%
Design - 80%
Construction - 60%
Construction Manager
Merry Anna Valdez
Project Scheduler Hill International, Inc.
Project Committee
Scott Cooper, Assistant Fire Chief, Design Advisor
Renee Wassenaar, Contract and Procurement Advisor
Charles Westover Project Manager
Hill International, Inc.
D-B RFQ/RFP - 30%
Design - 100%
Construction - 10%
Gregory Heinz Principal-in-Charge Hill International, Inc.
D-B RFQ/RFP - 10%
Design - 5%
Construction - 5%
D-B RFQ/RFP - 10%
Design - 10%
Construction - 10%
Construction Manager
Beau Bakken
Project Director
Fire Chief
North Mason Regional Fire Authority
Board of Commissioners
D-B RFQ/RFP - 10%
Design - On-call
Construction - On-call
Robynne Thaxton (Parkinson)
JD, DBIA DB Legal Counsel
Thaxton Parkinson, PLLC
Becky Blankenship Construction Manager
Hill International, Inc.
D-B RFQ/RFP - 100%
Design - 20%
Construction - 100%
Progressive
Design-Builder
Design - 100%
Construction - 100

## Slide 3: HQ Fire Station Facility Overview
Replace existing facility that no longer meets our needs
  New facility - approximately 20,200 SF
  Office and living space, including:
    Kitchen/dining area;
    Fitness room;
    Day room;
    Sleeping quarters;
    Indoor classes and training; and
    Apparatus bay for fire, ambulance and command vehicles

## Slide 4: Proposed HQ Fire Station Site

## Slide 5: HQ Fire Station Project Budget
  Professional Services $ 700,000
  Construction Cost $ 7,100,000
  Off-site Costs $ 360,000
  Contract Admin/Other $ 200,000
  NMRFA Contingency $ 700,000
  Other Related Project Expenses $ 150,000
  WSST $ 790,000
  Total Project Cost $ 10,000,000

## Slide 6: Schedule
  D-B RFQ Advertisement Apr 02, 2020
  D-B SOQ Due Apr 29, 2020
  Shortlist Finalists May 06, 2020
  Issue RFP May 12, 2020
  DB Team/Owner Interactive Mtg May 18, 2020
  Proposal Due May 26, 2020
  DB Team Interviews Jun 10, 2020
  Selection of DB Team June 22, 2020
  NTP Jul 2020
  Set GMP Jan 2020
  Construction Phase Jan 2021 thru Mar 2022

## Slide 7: Procurement Approach
  Request for Qualifications
    Successful Experience with Projects of Similar Scope and Complexity – Fire Stations or other Municipal facilities with unique equipment or functions
    Team Organization
    Experience developing GMP collaboratively with Owner
    Shortlist no more than three finalists
    History in soliciting and/or utilizing OMWBE subcontractors
  Request for Proposal
    Management approach specific to the project
    Innovation and Problem Solving
    Interactive Proprietary Meetings
    Statutorily required evaluation factors
    Price related factor: Fee
    $5,000 honorarium
      Limited required proposal submittals
      Consistent with other projects

## Slide 8
Design-Build Agreement
  Phase 1 - Validation and GMP Development Period
  Validate information from the Owner
  Examine options to identify innovation
  Commercially reasonable examination of site
  Develop Basis of Design Documents, Project Schedule, GMP
  Contract Amendment
  2. Phase 2 - GMP Execution Period
Complete Design
Construction
Close out

## Slide 9
Benefits of Design-Build Delivery
RCW 39.10.300(1)(b) “Greater Innovation or efficiencies between the designer and the builder”
  Maximum possibility for coordination of design and construction phasing to provide greatest project value, cost efficiency and design for specialized fire equipment and processes.
RCW 39.10.300 (1)(c) “significant savings in project delivery time”
  Progressive Design-Build is the fastest delivery method. Starting construction work prior to completion of design results in a significantly reduced schedule.
  An earlier completion date for the NMRFA HQ Fire Station will allow greater efficiency in emergency response services at an earlier date. This is critical for serving a broader portion of the community as soon as possible.
RCW 39.10.280(2)(a) “Substantial Fiscal Benefit”
  The budget is limited to fit within the Fire Authority’s project budget. The Design-Builder will be required to design within that budget.
  The Design-Builder’s involvement in the development of the scope shifts more risk of the performance of the project to the design-build team.
  With one team managing the coordination of the various aspects of the project, the Fire Authority’s risk of claims by various contractors performing adjacent projects are reduced.

## Slide 10
Additional Questions
QUESTION
The relationship of the Design-Builder to those listed in the organization chart is unclear.
RESPONSE
Organization chart has been updated to clarify the relationship of the Design-Builder to the rest of the project team.

## Slide 11
Additional Questions
QUESTION
Was an Independent Cost Estimator considered for this project?
RESPONSE
During our early programming phase, we engaged an Independent Cost Estimator to validate our initial target budget. For the next project phase, we’ve included a cost estimator on our team, as shown on our Organizational Chart. Aaron Aston is an employee of our 3rd party consultant, Hill International. He has recent experience with fire stations and with many other projects in the greater Seattle area, and is highly familiar with construction cost trends as they pertain to the proposed project.

## Slide 12
Additional Questions
QUESTION
What level of construction contingencies is included in the Project Budget on Page 1 of 8?
RESPONSE
We are at a very conceptual phase in planning for this project, so the breakdown shown on Page 1 is only an estimate. At this time we have assumed a construction contingency of 5% to 6%, and we expect the allocations of cost will change as we align the design with the GMP.

## Slide 13
Thank you!