## Slide 1
Application for Project Approval
Snohomish County
North Sound Behavioral Health Treatment Facility
Notes: Dave
Thank you,
Introduce attendees
Jennifer
Who the building serves
Why is the project needed
2 minutes

## Slide 2: Agenda
  Scope
  Schedule
  Budget and Funding
  Team
  Meets Statute Requirements
  Questions
Notes: Dave
Reviews agenda

## Slide 3: Scope
Notes: Chris
Brief comment on location
15 seconds

## Slide 4: Scope North Sound Behavioral Health Treatment Facility
Notes: Chris
Review current process on user programming and scoping efforts
Site constraints
2 minutes

## Slide 5: Scope
Addition & Renovation to the North Wing of the Existing Denney Juvenile Justice Facility
Addition SF: 10,201
Renovation SF: 13,732
Total SF: 23,933
Two Separately Operated 16-bed Facilities
Shared Clinical Support, Administrative Functions, Facility Support Services
Notes: Chris
Outline overall project scope
County’s focus on delivery, tight budget, program
Work at occupied building
Potential for construction impact on users
Starting entitlement process (pre-app, SEPA, NCU modification)
2 minutes

## Slide 6
Schedule
SCHEDULE EVENT | START | FINISH
PRC Application | 4/20/2018 | 4/20/2018
PRC Meeting | 5/24/2018 | 5/24/2018
Preliminary Design | 1/5/2018 | 4/25/2018
GCCM Procurement & Contracting | 5/25/2018 | 7/24/2018
Design | 4/26/2018 | 1/11/2019
Final Estimate and Validation | 1/12/2019 | 2/11/2019
Negotiate GMP / Approval | 2/12/2019 | 3/14/2019
Construction | 3/15/2019 | 3/14/2020
Cx / Systems Training / Shake-down | 3/15/2020 | 4/14/2020
Move-in, Furnish, Set-up, Closeout | 4/15/2020 | 6/14/2020
Notes: Dave
Overview schedule,
Early assembly of team to focus on
  Budget, Scope, Design and Construction Delivery
MCCM / ECCM team assembly to work with design team on best / efficient systems
2 minutes

## Slide 7: Budget
Costs for professional services (A/E, legal, Cx, testing & inspections etc.) | $1,500,000
Estimated project construction costs (including construction contingencies): | $9,500,000
Equipment and furnishing costs | $600,000
Off-site costs | $500,000
1% for art | $95,000
Contract administration costs (owner, cm, etc.) | $750,000
Contingencies (design & owner) | $950,000
Sales tax | $1,105,000
Total approved budget | $15,000,000
Notes: Jennifer
Overview of funding authorization
User / stakeholder group communication & coordination
Dave
Development budget put together, tight, $15M
Early scope and budget definition / confirmation is critical to the success of the project.
GCCM team on board early will assist in design / scope decision making to help guide the design to maintain budgets
Strong GCCM with tested preconstruction experience
Immediate budget / scoping evaluation after award
2 minutes

## Slide 8
Project Team
Notes: Jeff
Review project team focus on:
Managing users, stakeholders
OAC augmenting SnoCo with juvenile justice, healthcare, GCCM expertise, PM support and day / day management of teams
KMD strong behavioral health expertise, excellent designers, collaborative team (Skagit Valley 2003 GCCM)
MCCM / ECCM involved early with MEP designers to facilitate early design, long lead procurement, possible design assist delivery of documents.
2 minutes

## Slide 9: Project Management Expertise
Kenmore’s downtown development
Project Leadership
  Jeff Hencz—Snohomish County
    Special Projects Manager
    30 year industry veteran
    Extensive negotiated delivery experience
    GCCM trained and Courthouse experience
  Dave Jobs—OAC Services, Inc.
    Sr. Associate, Program Manager
    25 year industry veteran
    DBIA Certified, CCM, extensive alternative delivery experience
    Healthcare and Juvenile Justice
  Chris Rubright—KMD Architects
    Principal, Director of Healthcare Planning
    30 year industry veteran
    Behavioral health
    GCCM delivery
Notes: Jeff
Highlight leadership team of Jeff, KMD and OAC
Collaborative efforts
Jeff and OAC have worked together for 5 years
KMD…add Chris
1 minute

## Slide 10: Project Management Expertise
Project Support
  Dan Chandler, OAC Services
    Principal
    30 years industry experience
    Extensive alternative delivery expertise
    Healthcare and Juvenile Justice
  John Parnass, Pacifica Law Group
    Partner
    Extensive GCCM expertise
Notes: Dave / Jeff
Highlight support team of GCCM experts
Dan and John involvement:
  RFQ, agreement and selection process
  Dan will provide advisory support if needed
  John will provide guidance to County
30 seconds

## Slide 11: Exceeds Statute Requirements
RCW 39.10
Complex phasing and scheduling
Addition and renovation to existing, operating and secure facility
GCCM involvement in design is critical
Project involves complex and technical environment
Notes: Dave
Talk about how this project meets criteria for GCCM delivery
2 minutes

## Slide 12: Public Benefit
RCW 39.10
Increase predictability of delivery and reduce financial risks
Likely to attract a more highly qualified construction team
Planning, coordinating and executing complex building systems is best done with collaboration between designers and builders
Notes: Dave
Expand on bullet points
1 minute

## Slide 13: PRC Application for Project Approval
Questions?
Notes: Dave
1 minute