## Slide 1
Public Facilities District (SPFD) INB Renovation Project
August 23, 2017
SPOKANE
PUBLIC FACILITIES
DISTRICT

## Slide 2: INB Performing Arts Overview
Constructed for the 1974 Worlds Fair
Ready for a renovation
  ADA compliance: meeting requirements in a timely manner
  Scopes: Auditorium, Back Stage, Lobby, Music Room and Building Systems
  Very limited 180 day construction window
  Must complete work to not impact operations
  Fixed GMP/flexible scope
  DB to collaborate with Owner regarding which scopes of work to complete

## Slide 3: Organizational Chart

## Slide 4: INB Performing Arts Project Budget
  Professional Services $ 75,000
  Design/Constr. Cost $ 17,200,000
  Contract Admin/Other $ 50,000
  Equipment/Furnishing $ 100,000
  Contingencies $ 878,000
  Other Related Project Expenses $ 183,500
  Sales Tax $ 1,513,500
  Total Project Cost $ 20,000,000

## Slide 5: Updated Schedule
  Issue PDB RFQ Aug 24, 2017
  Statement of Qualification Due Sep 08, 2017
  Short-List Announced Sep 12, 2017
  RFP Issued Sep 15, 2017
  Proprietary Meeting Sep 29, 2017
  Proposal Due Oct 06, 2017
  Selection of Design-Builder Oct 10, 2017
  Anticipate NTP Oct 18, 2017
  Design Phase Oct 19, 2017 – Jul 02, 2018
  Construction Phase May 01, 2018 – Oct 26, 2018
  Closeout Phase Oct 29, 2018 – Dec 31, 2018

## Slide 6: Procurement Approach
  Request for Qualifications
    Success with Renovation Projects of Similar Scope
    Team Expertise with Similar Buildings and Systems
    Experience in developing GMP collaboratively
    Shortlist no more than three finalists
  Request for Proposal
    Management approach specific to the project
    Innovation and Problem Solving
    Interactive Proprietary Meetings
    Price related factor: DB Fee
    Honorarium
      Limited required proposal submittals
      Consistent with other projects

## Slide 7: Design-Build Agreement
  Validation and GMP Development Period
  Examine and Validate information from the Owner
  Commercially reasonable examination of building
  Identify innovation and Develop Basis of Design Documents, Project Schedule, and GMP
  Agree on GMP Contract Amendment
  2. GMP Execution Period
Complete Design
Construction
Close out

## Slide 8: Benefits of Design Build Delivery
RCW 39.10.280(2)(a) “Substantial Fiscal Benefit”
  Limited budget to deliver the District’s project scope. The Design-Builder must possess specialized building knowledge and construction expertise.
  The Design-Builder’s early involvement mitigates design/construction risk to the owner and the design-build team.
RCW 39.10.300(1)(b) “Greater Innovation or efficiencies between the designer and the builder”
  By maximizing coordination of design, limited demolition and construction phasing there should be timely project delivery and cost efficiency.
RCW 39.10.300 (1)(c) “significant savings in project delivery time”
  Progressive Design-Build is the fastest PW delivery method. Ordering long lead items prior to completion of design is beneficial to the schedule.
  Design-Builder input on “means and methods” will further work within proposed schedule.

## Slide 9
Thank you!
SPOKANE
PUBLIC FACILITIES
DISTRICT