## Slide 1: Modern Application of the Spearin Doctrine
Robynne T. Parkinson
Thaxton Parkinson pllc

## Slide 2: Spearin: Why You Warrant What You Don’t Know
Robynne T. Parkinson
Thaxton Parkinson pllc

## Slide 3: Spearin: “I do not think that means what you think that means.”
Robynne T. Parkinson
Thaxton Parkinson pllc

## Slide 4: Risks on a Construction Project
Risk | Mitigation
Safety | Worker’s Compensation and Commercial General Liability
Defective Design | Professional Errors and Omissions
Defective Construction | Managed risk with some CGL coverage for resultant damage
Damage to the Work | Builder’s Risk

## Slide 5: Spearin v. US, 39 S. Ct. 59 (1918)
Construction of a dry dock at a Naval ship yard
Plans showed relocation of a sewer and had prescriptive drawings directing Spearin how to perform the work
Relocated sewer diverted water into a section of the sewer with an unknown obstruction, and a heavy rain combined with high tide caused the obstructed sewer to break
Spearin claimed additional money and walked off the job
US defended that Spearin’s obligation to investigate the site shifted the risk of the site conditions to Spearin.

## Slide 6: Spearin Ruling
“[T]he insertion of the articles prescribing the character, dimensions and location of the sewer imported a warranty that if the specifications were complied with, the sewer would be adequate. This implied warranty is not overcome by the general clauses requiring the contractor to examine the site, to check up the plans, and to assume responsibility for the work until completion and acceptance.3 The obligation to examine the site did not impose upon him the duty of making a diligent inquiry into the history of the locality with a view to determining, at his peril, whether the sewer specifically prescribed by the government would prove adequate.”

## Slide 7: Spearin Requirements
The contract contained prescriptive requirements
  Design
  Sole Source
  Representation (such as existing conditions)
The prescriptive requirements were reliable
  There is no disclaimer or bidders do not have sufficient opportunity or access to investigate
  The contractor does not actually know that the prescriptive requirements are unreliable

## Slide 8: Applications of Spearin
Prescriptive drawing
Prescriptive specification
Differing site conditions
Sole Source
  Specified Product
  Specified Subcontractor
  Refusal to agree to reasonable substitution
Market conditions

## Slide 9: Owner’s Risk
Professional standard of care does not produce perfect drawings
  Care and skill of professional in that profession at that time in that place
  Owners fall within “liability gap” between negligence and Spearin
Disallowing reliance increases cost
Shifting risk of plans requires loss of control

## Slide 10: Design-Build
Owner provides performance rather than prescriptive specification
Design-Builder carries the risk of the performance of the project
Design-Builder selected largely on qualifications

## Slide 11: GC/CM
Owner provides prescriptive specifications with some performance
Contractor selected early and provides constructability and value engineering analysis
Contractor selection is focused on qualifications
Subcontractor selection
  Limited prequalification (mechanical and electrical subcontractors)
  Hard money bid

## Slide 12: M.A. Mortenson Co. (1993)
Design-build of Air Force medical clinic
Design-Builder entitled to rely on 30% bridging documents
Corps rejected request for equitable adjustment when quantities in bridging documents were low
Board agreed that Corps had warranted information

## Slide 13: M.A. Mortenson Co. ASBCA No. 39978 (1993)
The contract required appellant to verify and validate the design as part of the design work, not the proposal effort.
At its most basic, the Government's interpretation is that appellant assumed the risk of any cost growth in connection with the structural concrete and reinforcing steel when it agreed to a fixed price for the construction phase. As the Government recognizes, this interpretation effectively reads the Changes clause out of the contract.

## Slide 14: Donahue Electric (2002)
VA Ambulatory Care Center
Specified boiler did not work with specified sterilizer
VA argued that design-builder responsible
“Specifications included in a design/build contract, however, to the extent specific requirements, quantities and sizes are set forth in those specifications, place the risk of design deficiencies on the owner.”

## Slide 15: Metcalf v. US, 742 F3d 984 (2014)
102 Fed. Cl. 334 (2011)
Military housing project
Demolition, design and construction of 212 housing units in Kaneohe Bay, HI
Total Contract Price $48.3 million
Metcalf claims costs in excess of $78 million
NAFAC interfered with Design-Builder’s work through excessive inspections and incompetent management.

## Slide 16: Metcalf v. US, 742 F3d 984 (2014)
Differing Site Conditions
  “Nothing in the contract’s general requirements that Metcalf check the site as part of designing and building the housing units, after the contract was entered into, expressly or implicitly warned Metcalf that it could not rely on, and that instead it bore the risk of error in, the government’s affirmative representations about the soil conditions. To the contrary, the government made those representations in the RFP and in pre-bid questions-and-answers for bidders’ use in estimating costs and therefore in submitting bids that, if accepted, would create a binding contract. The natural meaning of the representations was that, while Metcalf would investigate conditions once the work began, it did not bear the risk of significant errors in the pre-contract assertions by the government about the subsurface site conditions.”

## Slide 17: Metcalf v. US, 742 F3d 984 (2014)
Covenant of Good Faith and Fair Dealing
  “The government suggests a much more constraining view when it argues, for example, that there was no breach of the implied duty because “Metcalf cannot identify a contract provision that the Navy’s inspection process violated.” Gov’t Br. 16. That goes too far: a breach of the implied duty of good faith and fair dealing does not require a violation of an express provision in the contract.”

## Slide 18: Attempts to Avoid Spearin
Owners include performance/design-build requirements in design-bid-build projects
  Fire suppression, HVAC, electrical
Owner requires contractors to guarantee and warrant plans
  Low bid procurement: public contractors may not have expertise to actually warrant the plans
  Contractors do not carry errors and omissions
Owners require “Highest” standard of care from designers
Owners do not allow reliance on information in procurement
  Lump sum bid contains increase cost for risk with no audit
  Greater fool theory
Design-build delivery
GC/CM delivery

## Slide 19: Managing Risk
Intelligent and meaningful analysis of the risk
Select the proper procurement method
Accept risk where appropriate
Use commercially reasonable contracting terms
No one wins a contract

## Slide 20: Thaxton Parkinson PLLC
Robynne Parkinson is a Seattle based lawyer who provides legal services to a full range of clients performing construction work, including Owners, Contractors, Design Builders, Engineers and Architects. Robynne is one of the leading experts in construction law and alternative procurement both in Washington State and on a national basis. She serves on the National Design Build Institute of America Board of Directors and the American Arbitration Association National Construction Dispute Resolution Committee. In addition, she is co-chair of the DBIA National Legal and Legislation Committee and was instrumental in revising the DBIA form Design-Build contracts and subcontracts. She represented both the DBIA and the AIA in the amicus brief in the Metcalf v. US case. She served as the President of the Northwest Region for DBIA from 2008 to 2010 and continues on its Board of Directors as the co-chair of the Legislation Committee. Robynne was named as a Washington Super Lawyer in 2010-2014 and is one of the few lawyers who are Designated Design-Build Professionals. Robynne received her undergraduate degree from the University of Texas at Austin and her law degree from the University of Colorado, Boulder School of Law.
9311 SE 36th St., Suite 103
Mercer Island, Washington 98040
(206)909-5290
www.rtp-law.com
www.designbuildlaw.blogspot.com
e-mail: rparkinson@rtp-law.com.com